## MMM - Maintenance OS (hidden)
MONITORING OF MAINTENANCE JOB OUTSTANDING
|  | PT. HSL |  |  |  | Close | 19 | 47.5% | Point 1 | Point 5
|  | Mill : MMM |  |  |  | Open | 21 | 52.5% | 0 | 10
Periode 2019/2020
No | Opening Date | Station | Account | Equipment | Outstanding Job | PIC | Priority | Date line | Closing date | Status | Point | Remarks | Progress Job (%)
1 | 2019-06-26 | Clarification | 08SOL001 | #REF! | Instal pipa drain sludge tank ke parit dalam clarification, pipa 6 inch | Jetro | B | 2019-07-08 | 2019-07-02 | Close | 5 |  | 100%
2 | 2019-06-26 | Threshing | 04TPL007 | #REF! | Setting ulang timer tuangan tippler | Welman | A | 2019-06-28 | 2019-06-27 | Close | 5 |  | 100%
3 | 2019-06-25 | Press | 05VSC003 | #REF! | Ganti bearing vibrating screen No. 3 | Welman | A | 2019-06-26 | 2019-06-26 | Close | 5 |  | 100%
4 | 2019-06-01 | Kernel | 07HDC001 | #REF! | Buat tangga akses hydrocyclone | Jetro | B | 2019-07-31 |  | Open | 0
5 | 2019-06-01 | Boiler | 09BBL001 | #REF! | Pasang guard / penghalang naik ke tangga chamber | Jetro | B | 2019-07-31 |  | Open | 0
6 | 2019-06-01 | Depericarping | 06NPD001 | #REF! | Tambah pagar keliling nut polishing drum | Jetro | B | 2019-08-30 |  | Open | 0 | temuan genco faizal / BULT
7 | 2019-06-24 | Press | 05PRS001 | #REF! | Penggantian cage screw press | Jetro | A | 2019-06-30 | 2019-06-26 | Close | 5 |  | 100%
8 | 2019-06-27 | Press | 05FWC010 | #REF! | Bongkar Iclined loose fruite scrapper | Jetro | B | 2020-05-31 |  | Open | 0
9 | 2019-06-24 | WTP | 15SFP006 | #REF! | Tiping pipa untuk untreated WTP | Jetro | B | 2019-07-31 |  | Open | 0
10 | 2019-06-24 | Loading Ramp | 01LRA001 | #REF! | Ganti plate loading ramp line 1 | Sugianto | A | 2019-07-15 |  | Open | 0 |  | 50%
11 | 20 Juni 2019 | Storage Tank | 13CPP010 | #REF! | Pasang plate form despatch area | Jetro | B | 2019-07-06 | 2019-06-28 | Close | 5 |  | 100%
12 | 2019-06-26 | Storage Tank | 13CPP008 | #REF! | Pembuatan rantai untuk valve area despatch | Jetro | A | 2019-06-28 | 2019-06-28 | Close | 5 |  | 100%
13 | 2019-06-26 | Laboratorium | 30LCH002 | #REF! | Pembuatan kotak SOP 2 pcs | Jetro | B | 2019-06-30 | 2019-06-28 | Close | 5 |  | 100%
14 | 2019-06-24 | Boiler | 09BWT027 | #REF! | Overhaule softener no. 1 | Dedi | B | 2019-07-15 |  | Open | 0 |  | 45%
15 | 2019-06-25 | Press | 05FWC009 | #REF! | Perbaikan gearbox dan hanger bushing | Jetro | A | 2019-06-30 | 2019-06-26 | Close | 5 |  | 100%
16 | 2019-06-27 | Sterilizer | 03STR002 | #REF! | Perbaikan kebocoran pipa condensate Str. 2 | Jetro | A | 2019-06-27 | 2019-06-27 | Close | 5 |  | 100%
17 | 2019-06-27 | Clarification | 08SOL007 | #REF! | Tambal pipa sludge efluent pump | Jetro | A | 2019-06-27 | 2019-06-27 | Close | 5 |  | 100%
18 | 2019-06-27 | Boiler | 09BFC013 | #REF! | perbaikan flate atas body | Jetro | A | 2019-06-27 | 2019-06-27 | Close | 5 |  | 100%
19 | 2019-06-24 | WTP | 15SFP006 | #REF! | Perbaikan flow meter sumbat | Jetro | A | 2019-06-30 |  | Open | 0
20 | 2019-06-24 | Laboratorium | 30LCH002 | #REF! | Instal bunch crusher | Dedi | B | 2019-06-30 | 2019-06-26 | Close | 5 |  | 100%
21 | 2019-06-24 | WTP | 15SFP003 | #REF! | Overhaule sand filter 3 | Dedi | B | 2019-08-17 |  | Open | 0
22 | 2019-06-24 | Laboratorium | 30LCH002 | #REF! | Pemasangan cover parit WTP | Dedi | B | 2019-07-19 |  | Open | 0
23 | 2019-06-24 | Boiler | 09BWT028 | #REF! | Pengecekan resin softener no.2 | Jetro | B | 2019-06-30 |  | Open | 0
24 | 2019-06-24 | Storage Tank | 11CPT004 | #REF! | Perbaikan kebocroan pipa steam | Jetro | A | 2019-07-16 |  | Open | 0
25 | 2019-06-28 | Storage Tank | 11CPT006 | #REF! | Perbaikan lampu sorot storage tank no 6 | Welman | A | 2019-07-05 | 2019-06-30 | Close | 5 |  | 100%
26 | 2019-06-01 | Power House | 10mcc001 | #REF! | Ganti dan retighten bolt fuse Cubical Mill | Welman | A | 2019-07-31 |  | Open | 0 | temuan GRC
27 | 2019-06-28 | Press | 05PRS013 | #REF! | Ganti oil seal digester no 2 | Jetro | B | 2019-08-31 |  | Open | 0
28 | 2019-06-28 | Threshing | 04TRE003 | #REF! | ganti oil seal gearbox thresher no 3 | Jetro | B | 2019-08-31 |  | Open | 0
29 | 2019-06-28 | Threshing | 04TRE004 | #REF! | ganti oil seal gearbox thresher no 4 | Jetro | B | 2019-08-31 | 2019-07-04 | Close | 5 |  | 100%
30 | 2019-06-28 | Clarification | 08CST001 | #REF! | pasang pipa overflow CST no 1 | Jetro | B | 2019-08-31 |  | Open | 0
31 | 2019-06-28 | Clarification | 08CST001 | #REF! | pabrikasi dan pasang pipa underflow | Jetro | B | 2019-08-31 |  | Open | 0
32 | 2019-06-28 | Clarification | 08SOL007 | #REF! | pabrikasi dan pasang pipa sludge tank | Jetro | B | 2019-08-31 | 2019-07-02 | Close | 5 |  | 100%
33 | 2019-06-28 | Clarification | 09BWT047 | #REF! | pabrikasi dan pasang pipa air klarifikasi | Jetro | B | 2019-08-31 |  | Open | 0
34 | 2019-06-28 | Kernel | 06NDA021 | #REF! | pabrikasi dan pasang chute fibre cyclone | Jetro | B | 2019-08-31 |  | Open | 0
35 | 2019-06-28 | Press | 05PRS014 | #REF! | tinggikan bottom plate digester no 3 | Jetro | B | 2019-08-31 |  | Open | 0
36 | 2019-06-27 | Press | 05PRS024 | #REF! | Perbaikan kebocoran pipa | Jetro | B | 2019-07-19 | 2019-06-28 | Close | 5 |  | 100%
37 | 2019-06-27 | Sterilizer | 03DWB023 | #REF! | Perbaikan pipa hydraulic str no. 3 | Jetro | A | 2019-06-30 | 2019-06-28 | Close | 5 |  | 100%
38 | 2019-06-27 | Press | 02UDS006 | #REF! | Perbaikan sprocket undertow tippler line 2 | Jetro | B | 2019-07-06 |  | Open | 0
39 | 2019-06-27 | Press | 05PRS001 | #REF! | Adjust vee belt motor yang kendor | Jetro | A | 2019-06-28 | 2019-06-27 | Close | 5 |  | 100%
40 | 2019-06-27 | Threshing | 04TRE002 | #REF! | Perbaikan kisi-kisi drum thresher no. 2 | Jetro | A | 2019-06-28 | 2019-06-28 | Close | 5 |  | 100%
41 | 2019-06-30 | Sterilizer | 03STR003 | #REF! | Perbaikan Packing pintu masuk sterilizer 3 | Jetro | A | #REF! | #REF! | #REF! | #REF! |  | 100%
42 | 2019-06-30 | Kernel | 07HDC002 | #REF! | Rantai Hydro Cyclone Putus | Jetro | A | #REF! | #REF! | #REF! | #REF! |  | 100%
43 | 2019-07-03 | Kernel | 06NDA021 | #REF! | Pengarah Angin Fan Jatuh | Jetro | A | 2019-07-04 | #REF! | #REF! | #REF! |  | 100%
44 | 2019-07-03 |  | 04TPL007 | #REF! | Besi koyak di wet area | Jetro | B | 2019-07-04 | #REF! | #REF! | #REF! |  | 100%
45 | 2019-07-03 | Loading Ramp | 02CBD002 | #REF! | Baut Elmo dengan pondasi lepas | Jetro | B | 2019-07-04 | #REF! | #REF! | #REF! |  | 100%
46 | 2019-07-03 | Press | 04SFB016 | #REF! | Tambah Oli | Jetro | B | 2019-07-04 | #REF! | #REF! | #REF! |  | 100%
Formulas:
Opening Date = [Opening Date, row above]
Note on I5: Normansyah Simorangkir: Harus didiskusikan antara tim proses dan tim maintenance
Note on J5: Normansyah Simorangkir: Harus diisi
Note on N5: Dedi Suryawardana:

## MWO (hidden)
| PT. HSL, MANIS MATA MILL | [5 empty] | Total Job | 1 | 1 | =Done
| MWO LIST | [5 empty] | Complete Progress | 0% | 0 | =Not Done
=NA
| No | Station | Equipment | Description | Issued | Execution | Man Power | Status | Keterangan
| 1 | Clarification | Sludge Balance Tank | Instal pipa drain sludge tank ke parit dalam clarification, pipa 6 inch
|  | Tippler | Tippler No.2 | Setting ulang timer tuangan tippler
|  | Press | Screw Press Hydraulic Pack No.4 | Ganti bearing vibrating screen No. 3
|  | Kernel | Hydrocyclone Dripping Drum No. 1 | Buat tangga akses hydrocyclone
|  | Boiler | Boiler Blowdown Chamber | Pasang guard / penghalang naik ke tangga chamber
|  | Kernel | Nut Polishing Drum No.1 | Tambah pagar keliling nut polishing drum
|  | Press | Screw Press No. 1 | Penggantian cage screw press
|  | Press | Inclined Loose Fruit Scrapper | Bongkar Iclined loose fruite scrapper
|  | WTP | Piping raw water | Tiping pipa untuk untreated WTP
|  | Loading Ramp | Loading ramp 1 | Ganti plate loading ramp line 1
|  | Storage Tank | Despatch area | Pasang plate form despatch area
103

## Dbase Sunday SDT WList FY1920
Cargill Tropical Crush | [23 empty] | HW: Hot Work
FY1819 | [13 empty] | Mill | MANIS MATA |  |  |  | Total Planned Works |  | 20 |  |  | LO: Lock Out
Sunday SDT Worklist | [18 empty] | Number of works completed |  | 90% |  |  | EL: Elev Work
CV: Confine Space
Month | Date | Source | Category | Scope | Scope | No | Station | Equipment | Work Description | Priority | Manpower Planning |  |  |  | Time |  |  |  | Required permit(s) | Actual |  | Remark | Category | LR: Lifting Rigging
[11 empty] | Name | Employee OR Contractor | No of Manpower | Supervised by | Start | Finish | Total Required Hours | Actual Spent Hours |  | Done | Not Done |  |  |  | Month | Number of Proposed Work | Number of Work Done | % Done
Juni-018 | [23 empty] | 2020-06-07 | 2020-06-01 | 0 | 0 | #DIV/0!
Juni-018 | [24 empty] | 2020-07-01 | 0 | 0 | #DIV/0!
Juni-018 | [24 empty] | 2020-08-01 | 0 | 0 | #DIV/0!
Juni-018 | [24 empty] | 2020-09-01 | 16 | 14 | 87.5%
[25 empty] | 2020-10-01 | 4 | 4 | 100%
[25 empty] | 2020-11-01 | 0 | 0 | #DIV/0!
[25 empty] | 2020-12-01 | 0 | 0 | #DIV/0!
Juni-018 | [23 empty] | 2020-06-14 | 2021-01-01 | 0 | 0 | #DIV/0!
[25 empty] | 2021-02-01 | 0 | 0 | #DIV/0!
[25 empty] | 2021-03-01 | 0 | 0 | #DIV/0!
[25 empty] | 2021-04-01 | 0 | 0 | #DIV/0!
[25 empty] | 2021-05-01 | 0 | 0 | #DIV/0!
[25 empty] | FY1920 | 20 | 18 | 90%
Juni-018
Juni-018
Juni-018 | [23 empty] | 2020-06-21
Juni-018
Juni-018
Juli-018 | [23 empty] | 2020-06-28
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018 | [23 empty] | 2020-07-05
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018 | [23 empty] | 2020-07-12
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018 | [23 empty] | 2020-07-19
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018 | [23 empty] | 2020-07-26
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
Juli-018
2018-08-01
2018-08-01
2018-08-01
2018-08-01 | [23 empty] | 2020-08-02
2018-08-18 | [23 empty] | 2020-08-09
2018-08-18 | [23 empty] | 2020-08-16
2020-08-23
| 2020-08-30 |  |  |  |  | 1 | Sterilizer | Sterilizer | Instal pipe exhaust Sterilizer #1 | A | Manto, Hamzah | Employee and Contractor | 2 | Jetro S/Sugianto | 7 | 12 | 5 | 5 | Lo,Ho,Elv,Lift | 1 |  |  |  | 2020-08-30
| 2020-08-30 |  |  |  |  | 2 | Sterilizer | Sterilizer | Instal pipe Inlet Sterilizer #3 | A | Manto, Hamzah | Employee and Contractor | 2 | Jetro S/Sugianto | 12 | 17 | 5 | 5 | Lo,Ho,Elv,Lift | 1
| 2020-08-30 |  |  |  |  | 3 | Sterilizer | Sterilizer | Instal elbow pipe condensate Sterilizer | A | Kisyam, Roni | Employee | 2 | Jetro S/Sugianto | 7 | 12 | 5 | 8 | Lo,Ho,Elv,Lift | 1
| 2020-08-30 |  |  |  |  | 4 | Sterilizer | Sterilizer | Instal pipe exhaust Sterilizer #2 | A | Kisyam, Roni | Employee | 2 | Jetro S/Sugianto | 12 | 17 | 5 | 5 | Lo,Ho,Elv,Lift | 1
| 2020-08-30 |  |  |  |  | 5 | Klarifikasi | Treated Pipe | Change pipe water treated at klarification area | A | Indra, Ali, Sumadi | Employee and Contractor | 3 | Jetro S/Sugianto | 7 | 17 | 10 | 10 | Lo,Ho,Elv,Lift | 1
| 2020-08-30 |  |  |  |  | 6 | Kernel | Hydro Cyclone #2 | Perbaikan pengarah air vortex hydro cyclone #2 | B | Zainullah, Agus H | Employee and Contractor | 2 | Jetro S/Sugianto | 7 | 11 | 4 | 2 | Lo,Ho |  | 1 | Waktu tidak cukup untuk pemasangan pengarah
| 2020-08-30 |  |  |  |  | 7 | Kernel | Hydro Cyclone Drum | Perbaikan dinding drum hydro cyclone #1,2,3 | A | Zainullah, Agus H | Employee and Contractor | 2 | Jetro S/Sugianto | 11 | 17 | 6 | 2 | Lo,Ho | 1
| 2020-08-30 |  |  |  |  | 8 | Boiler | Fly ash Boiler | Penggantian bearing airlock fly ash boiler | A | Rodi H, Ujang R, Prasetya | Employee and Contractor | 3 | Jetro S/Sugianto | 11 | 15 | 4 | 4 | Lo,Ho | 1
| 2020-08-30 |  |  |  |  | 9 | Boiler | Fuel Feeder | Perbaikan Chute Fuel Feeder #1,2 | A | Suryono, Sarmo | Employee and Contractor | 2 | Jetro S/Sugianto | 13 | 17 | 4 | 10 | Ho,Elv,Lift | 1
| 2020-08-30 |  |  |  |  | 10 | Effluet | Effluent | Ganti Tee HDPE Limbah | A | Rodi H, Ujang R, Prasetya | Employee and Contractor | 3 | Jetro S/Sugianto | 7 | 11 | 4 | 2 | Lo, Ho | 1
| 2020-08-30 |  |  |  |  | 11 | WTP | Pompa Sand Filter | Perbaikan kebbocoran pompa Sand Filter | A | Rodi H, Ujang R, Prasetya | Employee and Contractor | 3 | Jetro S/Sugianto | 15 | 17 | 2 | 4 | Lo, Ho | 1
| 2020-08-30 |  |  |  |  | 12 | Boiler | Boiler | Instalasi Mobrey Chamber Boiler | A | Zisyam Didi | Employee and Contractor | 2 | Welmansyah/Sugianto | 7 | 11 | 4 | 4 | Lo,Ho | 1
| 2020-08-30 |  |  |  |  | 13 | Power House | MCC | Penggantian capasitor bank | A | Mufijar, Langseng | Employee | 2 | Welmansyah/Sugianto | 7 | 13 | 6 | 10 | Lo,Lift | 1
| 2020-08-30 |  |  |  |  | 14 | Boiler | Compressor | Instalasi air dryer compressor | A | Zisyam Didi | Employee | 2 | Welmansyah/Sugianto | 11 | 15 | 4 | 4 | Lo | 1
| 2020-08-30 |  |  |  |  | 15 | Boiler | Panel Boiler | EMP MCC/Panel Boiler | A | Zisyam Didi | Employee | 2 | Welmansyah/Sugianto | 15 | 17 | 2 | 2 | Lo | 1
| 2020-08-30 |  |  |  |  | 16 | Sterilizer | Sterilizer | Ganti pipa transmisi sterilizer #1,3,4 | B | Mufijar, Langseng | Employee | 2 | Welmansyah/Sugianto | 13 | 17 | 4 | 0 | Lo |  | 1 | Waktu tidak cuku karena pekerjaan penggantian capasitor bank memerlukan waktu lama
2019-09-16
2019-09-22
2019-09-29
2019-10-06
2019-10-13
2019-10-10
| 2020-10-25 |  |  |  |  | 17 | Threshing | Horizontal Empty Bunch no2 | OH Conveyor ( Ganti Sproket atas dan bawah ) | A | Rodi,Manto,Ali,Agus H | Employee and Contractor | 4 | Jetro S/Sugianto | 7 | 17 | 10 |  | Lo,Ho,Elv,Lift | 1 |  |  |  | 2020-10-25
| 2020-10-25 |  |  |  |  | 18 | Threshing | Horizontal Empty Bunch no2 | OH Conveyor ( Ganti Rantai & Scraper ) | A | Kisyam, Roni,Hamzah,Ujang Ridwan | Employee and Contractor | 4 | Jetro S/Sugianto | 7 | 17 | 10 |  | Lo,Ho,Elv,Lift | 1
| 2020-10-25 |  |  |  |  | 19 | Threshing | Horizontal Empty Bunch no2 | OH Conveyor ( Ganti liner rail ) | A | Indra,David,Edi Rusmani | Employee | 3 | Jetro S/Sugianto | 7 | 17 | 10 |  | Lo,Ho,Elv,Lift | 1
| 2020-10-25 |  |  |  |  | 20 | Boiler | Daerator Pump | Install Pipa ilnet pompa daerator pump no2 | A | Zainullah,Hery | Employee and Contractor | 2 | Jetro S/Sugianto | 7 | 17 | 10 |  | Lo,Ho, | 1
2019-11-04
2019-11-10
2019-11-17
2019-11-24
2019-12-08
2019-12-15
2019-12-22
2019-12-29
2020-01-05
2020-01-12
2020-01-19
2020-01-26
2020-02-02
2020-02-09
2020-02-16
2020-02-23
2020-03-01
2020-03-08
2020-03-15
2020-03-22
2020-03-29
2020-04-05
2020-04-12
2020-04-19
2020-04-26
2019-05-03
2020-05-10
2020-05-17
2020-05-24
2020-05-31

## 7-Juni-20
Cargill Tropical Crush
Sunday SDT Worklist | [12 empty] | Total Planned Works
|  |  |  | Date | 2020-06-07 |  |  | Mill Manis Mata |  |  |  |  | Number of works completed |  | 87.5%
No | Station | Equipment | Work Description | Priority | Manpower Planning |  |  |  | Time |  |  |  | Required permit(s) | Actual |  | Remark
[5 empty] | Name | Employee OR Contractor | No of Manpower | Supervised by | Start | Finish | Total Required Hours | Actual Spent Hours |  | Done | Not Done
Mechanical
Electrical

## 14-Juni-20
Cargill Tropical Crush
Sunday SDT Worklist | [12 empty] | Total Planned Works
|  |  |  | Date | 2020-06-14 |  |  | Mill Manis Mata |  |  |  |  | Number of works completed |  | 87.5%
No | Station | Equipment | Work Description | Priority | Manpower Planning |  |  |  | Time |  |  |  | Required permit(s) | Actual |  | Remark
[5 empty] | Name | Employee OR Contractor | No of Manpower | Supervised by | Start | Finish | Total Required Hours | Actual Spent Hours |  | Done | Not Done
Mechanical
1
2
3
4
5
Electrical
6
7
8
9
10
11

## 21-Juni-20
Cargill Tropical Crush
Sunday SDT Worklist | [12 empty] | Total Planned Works
|  |  |  | Date | 2020-06-21 |  |  | Mill Manis Mata |  |  |  |  | Number of works completed |  | 87.5%
No | Station | Equipment | Work Description | Priority | Manpower Planning |  |  |  | Time |  |  |  | Required permit(s) | Actual |  | Remark
[5 empty] | Name | Employee OR Contractor | No of Manpower | Supervised by | Start | Finish | Total Required Hours | Actual Spent Hours |  | Done | Not Done
Mechanical
1
2
3
4
5
Electrical
6
7
8
9
10
11

## 28-Juni-20
Cargill Tropical Crush
Sunday SDT Worklist | [12 empty] | Total Planned Works
|  |  |  | Date | 2020-06-28 |  |  | Mill Manis Mata |  |  |  |  | Number of works completed |  | 87.5%
No | Station | Equipment | Work Description | Priority | Manpower Planning |  |  |  | Time |  |  |  | Required permit(s) | Actual |  | Remark
[5 empty] | Name | Employee OR Contractor | No of Manpower | Supervised by | Start | Finish | Total Required Hours | Actual Spent Hours |  | Done | Not Done
Mechanical
1
2
3
4
5
Electrical
6
7
8
9
10
11

## 5-Juli-20
Cargill Tropical Crush
Sunday SDT Worklist | [12 empty] | Total Planned Works
|  |  |  | Date | 2020-07-05 |  |  | Mill Manis Mata |  |  |  |  | Number of works completed |  | 87.5%
No | Station | Equipment | Work Description | Priority | Manpower Planning |  |  |  | Time |  |  |  | Required permit(s) | Actual |  | Remark
[5 empty] | Name | Employee OR Contractor | No of Manpower | Supervised by | Start | Finish | Total Required Hours | Actual Spent Hours |  | Done | Not Done
Mechanical
1
2
3
4
5
Electrical
6
7
8
9
10
11

## 12-Juli-20
Cargill Tropical Crush
Sunday SDT Worklist | [12 empty] | Total Planned Works
|  |  |  | Date | 2020-07-12 |  |  | Mill Manis Mata |  |  |  |  | Number of works completed |  | 87.5%
No | Station | Equipment | Work Description | Priority | Manpower Planning |  |  |  | Time |  |  |  | Required permit(s) | Actual |  | Remark
[5 empty] | Name | Employee OR Contractor | No of Manpower | Supervised by | Start | Finish | Total Required Hours | Actual Spent Hours |  | Done | Not Done
Mechanical
1
2
3
4
5
Electrical
6
7
8
9
10
11

## 19-Juli-20
Cargill Tropical Crush
Sunday SDT Worklist | [12 empty] | Total Planned Works
|  |  |  | Date | 2020-07-19 |  |  | Mill Manis Mata |  |  |  |  | Number of works completed |  | 87.5%
No | Station | Equipment | Work Description | Priority | Manpower Planning |  |  |  | Time |  |  |  | Required permit(s) | Actual |  | Remark
[5 empty] | Name | Employee OR Contractor | No of Manpower | Supervised by | Start | Finish | Total Required Hours | Actual Spent Hours |  | Done | Not Done
Mechanical
1
2
3
4
5
Electrical
6
7
8
9
10
11

## 26-Juli-20
Cargill Tropical Crush
Sunday SDT Worklist | [12 empty] | Total Planned Works
|  |  |  | Date | 2020-07-26 |  |  | Mill Manis Mata |  |  |  |  | Number of works completed |  | 87.5%
No | Station | Equipment | Work Description | Priority | Manpower Planning |  |  |  | Time |  |  |  | Required permit(s) | Actual |  | Remark
[5 empty] | Name | Employee OR Contractor | No of Manpower | Supervised by | Start | Finish | Total Required Hours | Actual Spent Hours |  | Done | Not Done
Mechanical
1
2
3
4
5
Electrical
6
7
8
9
10
11

## 2-Agustus-20
Cargill Tropical Crush
Sunday SDT Worklist | [12 empty] | Total Planned Works
|  |  |  | Date | 2-Agustus-20 |  |  | Mill Manis Mata |  |  |  |  | Number of works completed |  | 87.5%
No | Station | Equipment | Work Description | Priority | Manpower Planning |  |  |  | Time |  |  |  | Required permit(s) | Actual |  | Remark
[5 empty] | Name | Employee OR Contractor | No of Manpower | Supervised by | Start | Finish | Total Required Hours | Actual Spent Hours |  | Done | Not Done
Mechanical
1
2
3
4
5
Electrical
6
7
8
9
10
11

## 9-Agustus-20
Cargill Tropical Crush
Sunday SDT Worklist | [12 empty] | Total Planned Works
|  |  |  | Date | 2-Agustus-20 |  |  | Mill Manis Mata |  |  |  |  | Number of works completed |  | 87.5%
No | Station | Equipment | Work Description | Priority | Manpower Planning |  |  |  | Time |  |  |  | Required permit(s) | Actual |  | Remark
[5 empty] | Name | Employee OR Contractor | No of Manpower | Supervised by | Start | Finish | Total Required Hours | Actual Spent Hours |  | Done | Not Done
Mechanical
1
2
3
4
5
Electrical
6
7
8
9
10
11

## 16-Agustus-20
Cargill Tropical Crush
Sunday SDT Worklist | [12 empty] | Total Planned Works
|  |  |  | Date | 2-Agustus-20 |  |  | Mill Manis Mata |  |  |  |  | Number of works completed |  | 87.5%
No | Station | Equipment | Work Description | Priority | Manpower Planning |  |  |  | Time |  |  |  | Required permit(s) | Actual |  | Remark
[5 empty] | Name | Employee OR Contractor | No of Manpower | Supervised by | Start | Finish | Total Required Hours | Actual Spent Hours |  | Done | Not Done
Mechanical
1
2
3
4
5
Electrical
6
7
8
9
10
11

## 23-Agustus-20
Cargill Tropical Crush
Sunday SDT Worklist | [12 empty] | Total Planned Works
|  |  |  | Date | 2-Agustus-20 |  |  | Mill Manis Mata |  |  |  |  | Number of works completed |  | 87.5%
No | Station | Equipment | Work Description | Priority | Manpower Planning |  |  |  | Time |  |  |  | Required permit(s) | Actual |  | Remark
[5 empty] | Name | Employee OR Contractor | No of Manpower | Supervised by | Start | Finish | Total Required Hours | Actual Spent Hours |  | Done | Not Done
Mechanical
1
2
3
4
5
Electrical
6
7
8
9
10
11

## 30-Agustus-20
Cargill Tropical Crush
Sunday SDT Worklist | [12 empty] | Total Planned Works |  | 16
|  |  |  | Date | 30-Agustus-20 |  |  | Mill Manis Mata |  |  |  |  | Number of works completed |  | 87.5%
No | Station | Equipment | Work Description | Priority | Manpower Planning |  |  |  | Time |  |  |  | Required permit(s) | Actual |  | Remark
[5 empty] | Name | Employee OR Contractor | No of Manpower | Supervised by | Start | Finish | Total Required Hours | Actual Spent Hours |  | Done | Not Done
Mechanical
1 | Sterilizer | Sterilizer | Instal pipe exhaust Sterilizer #1 | A | Manto, Hamzah | Employee and Contractor | 2 | Jetro S/Sugianto | 7 | 12 | 5 | 5 | Lo,Ho,Elv,Lift | 1
2 | Sterilizer | Sterilizer | Instal pipe Inlet Sterilizer #3 | A | Manto, Hamzah | Employee and Contractor | 2 | Jetro S/Sugianto | 12 | 17 | 5 | 5 | Lo,Ho,Elv,Lift | 1
3 | Sterilizer | Sterilizer | Instal elbow pipe condensate Sterilizer | A | Kisyam, Roni | Employee | 2 | Jetro S/Sugianto | 7 | 12 | 5 | 8 | Lo,Ho,Elv,Lift | 1
4 | Sterilizer | Sterilizer | Instal pipe exhaust Sterilizer #2 | A | Kisyam, Roni | Employee | 2 | Jetro S/Sugianto | 12 | 17 | 5 | 5 | Lo,Ho,Elv,Lift | 1
5 | Klarifikasi | Treated Pipe | Change pipe water treated at klarification area | A | Indra, Ali, Sumadi | Employee and Contractor | 3 | Jetro S/Sugianto | 7 | 17 | 10 | 10 | Lo,Ho,Elv,Lift | 1
6 | Kernel | Hydro Cyclone #2 | Perbaikan pengarah air vortex hydro cyclone #2 | B | Zainullah, Agus H | Employee and Contractor | 2 | Jetro S/Sugianto | 7 | 11 | 4 | 2 | Lo,Ho |  | 1 | Waktu tidak cukup untuk pemasangan pengarah
7 | Kernel | Hydro Cyclone Drum | Perbaikan dinding drum hydro cyclone #1,2,3 | A | Zainullah, Agus H | Employee and Contractor | 2 | Jetro S/Sugianto | 11 | 17 | 6 | 2 | Lo,Ho | 1
8 | Boiler | Fly ash Boiler | Penggantian bearing airlock fly ash boiler | A | Rodi H, Ujang R, Prasetya | Employee and Contractor | 3 | Jetro S/Sugianto | 11 | 15 | 4 | 4 | Lo,Ho | 1
9 | Boiler | Fuel Feeder | Perbaikan Chute Fuel Feeder #1,2 | A | Suryono, Sarmo | Employee and Contractor | 2 | Jetro S/Sugianto | 13 | 17 | 4 | 10 | Ho,Elv,Lift | 1
10 | Effluet | Effluent | Ganti Tee HDPE Limbah | A | Rodi H, Ujang R, Prasetya | Employee and Contractor | 3 | Jetro S/Sugianto | 7 | 11 | 4 | 2 | Lo, Ho | 1
11 | WTP | Pompa Sand Filter | Perbaikan kebbocoran pompa Sand Filter | A | Rodi H, Ujang R, Prasetya | Employee and Contractor | 3 | Jetro S/Sugianto | 15 | 17 | 2 | 4 | Lo, Ho | 1
Electrical
12 | Boiler | Boiler | Instalasi Mobrey Chamber Boiler | A | Zisyam Didi | Employee and Contractor | 2 | Welmansyah/Sugianto | 7 | 11 | 4 | 4 | Lo,Ho | 1
13 | Power House | MCC | Penggantian capasitor bank | A | Mufijar, Langseng | Employee | 2 | Welmansyah/Sugianto | 7 | 13 | 6 | 10 | Lo,Lift | 1
14 | Boiler | Compressor | Instalasi air dryer compressor | A | Zisyam Didi | Employee | 2 | Welmansyah/Sugianto | 11 | 15 | 4 | 4 | Lo | 1
15 | Boiler | Panel Boiler | EMP MCC/Panel Boiler | A | Zisyam Didi | Employee | 2 | Welmansyah/Sugianto | 15 | 17 | 2 | 2 | Lo | 1
16 | Sterilizer | Sterilizer | Ganti pipa transmisi sterilizer #1,3,4 | B | Mufijar, Langseng | Employee | 2 | Welmansyah/Sugianto | 13 | 17 | 4 | 0 | Lo |  | 1 | Waktu tidak cuku karena pekerjaan penggantian capasitor bank memerlukan waktu lama

## 25 Oktober-20
Cargill Tropical Crush
Sunday SDT Worklist | [12 empty] | Total Planned Works |  | 16
|  |  |  | Date | 25-Oktober-2020 |  |  | Mill Manis Mata |  |  |  |  | Number of works completed |  | 87.5%
No | Station | Equipment | Work Description | Priority | Manpower Planning |  |  |  | Time |  |  |  | Required permit(s) | Actual |  | Remark
[5 empty] | Name | Employee OR Contractor | No of Manpower | Supervised by | Start | Finish | Total Required Hours | Actual Spent Hours |  | Done | Not Done
Mechanical
1 | Threshing | Horizontal Empty Bunch no2 | OH Conveyor ( Ganti Sproket atas dan bawah ) | A | Rodi,Manto,Ali,Agus H | Employee and Contractor | 4 | Jetro S/Sugianto | 7 | 17 | 10 |  | Lo,Ho,Elv,Lift | 1
2 | Threshing | Horizontal Empty Bunch no2 | OH Conveyor ( Ganti Rantai & Scraper ) | A | Kisyam, Roni,Hamzah,Ujang Ridwan | Employee and Contractor | 4 | Jetro S/Sugianto | 7 | 17 | 10 |  | Lo,Ho,Elv,Lift | 1
3 | Threshing | Horizontal Empty Bunch no2 | OH Conveyor ( Ganti liner rail ) | A | Indra,David,Edi Rusmani | Employee | 3 | Jetro S/Sugianto | 7 | 17 | 10 |  | Lo,Ho,Elv,Lift | 1
4 | Boiler | Daerator Pump | Install Pipa ilnet pompa daerator pump no2 | A | Zainullah,Hery | Employee and Contractor | 2 | Jetro S/Sugianto | 7 | 17 | 10 |  | Lo,Ho, | 1
5
6
7
8
9
10
11
Electrical
12
13
14
15
16

## Sheet1 (hidden)
Lock Out Tag Out | LOTO, HotWork, Lifting Rigging, Confined Spaced, General Work
HOT Work | LOTO, HotWork, Lifting Rigging, Confined Spaced
Lifting Rigging | LOTO, HotWork, Elevated Work, General Work
Confined Spaced | LOTO, HotWork, Elevated Work
Elevated Work | LOTO, HotWork, General Work
Excavation | LOTO, HotWork, LiftingRigging
Chemical Handling | LOTO, HotWork, Confined Spaced, General Work
By Pass | LOTO, HotWork, Confined Spaced
General Work | LOTO, HotWork
LOTO, Elevated Work
LOTO, Confined Spaced, General Work
LOTO, Confined Spaced
LOTO
Elevated Work, HotWork, Lifting Rigging, General Work
Elevated Work, HotWork, Lifting Rigging
Elevated Work, HotWork, General Work
Elevated Work, HotWork
Elevated Work
Confined Spaced
Chemical Handling
By Pass
Lifting Rigging
HotWork
General Work